## Product Backlog
PRODUCT BACKLOG
FoodBridge - PRODUCT BACKLOG
ID | AS A … | I WANT TO … | SO THAT … | PRIORITY | Number of SPRINTs | STATUS | STORY POINTS | STATUS | PRIORITY | WRITTEN BY
US01 | donor | create an account | I can access the platform and start donating surplus food | High | 1 | Not Started | 3 | Not Started | High | Maryam Alqahtani
US05 | charity | register my organization with its name, license number and location | I can receive food donations through the platform | High | 1 | Not Started | 3 | In Progress | Medium | Ghala Alsowayan
US02 | registered user (donor or charity) | log in to my account | I can access and manage my donations or my donation requests | High | 1 | Not Started | 2 | Complete | Low | Maryam Alqahtani
US03 | donor | add a food donation with its relevant details | charities can view it and decide whether it meets their needs | High | 1 | Not Started | 5 | Overdue |  | Maryam Alqahtani
US06 | charity | browse the list of donations that are still available | I can find food that fits the needs of the families we serve | High | 1 | Not Started | 3 | On Hold |  | Ghala Alsowayan
US07 | charity | open a donation and see its details (food type, quantity, expiry time, pickup address) | I can decide if we are able to collect it before it expires | High | 2 | Not Started | 2 |  |  | Ghala Alsowayan
US08 | charity | send a request for an available donation | the donor knows that we want to collect it | High | 2 | Not Started | 3 |  |  | Ghala Alsowayan
US09 | donor | accept or reject a donation request | I can decide which charity will receive my food donation | High | 2 | Not Started | 5 |  |  | Albatool Hafez
US10 | donor | track the current status of each active donation | I know whether it is available, requested, accepted or collected without contacting the charity | Medium | 2 | Not Started | 3 |  |  | Albatool Hafez
US11 | donor | update the collection status of a donation | the platform reflects whether the donated food has been collected | Medium | 2 | Not Started | 2 |  |  | Albatool Hafez
US04 | donor | view, edit or delete my active donations (not yet collected) | the details charities see stay correct while the food is still available | Medium | 2 | Not Started | 5 |  |  | Maryam Alqahtani
US16 | charity | search and filter donations by food type, quantity and pickup area | I reach the suitable donations faster instead of scrolling the whole list | Medium | 2 | Not Started | 5 |  |  | Renad Alabdani
US15 (Epic) | donor or charity | be notified when something important changes in my donations or requests | I can act on time before the food goes bad | Low | 2 | Not Started | 8 |  |  | Renad Alabdani
US12 (Epic) | donor | view the history of my completed and expired donations | I can review my previous donations and which charities received them | Low | 2 | Not Started | 3 |  |  | Albatool Hafez
US13 (Epic) | admin | manage the user accounts on the platform (review, approve and deactivate donors and charities) | only real donors and licensed charities use the platform | Low | 2 | Not Started | 8 |  |  | Renad Alabdani
US14 (Epic) | admin | monitor all donation activity on the platform from an admin dashboard | I can follow the activity of the platform and spot problems early | Low | 2 | Not Started | 8 |  |  | Renad Alabdani
TOTAL | [6 empty] | 68