## PROJECT DETAILS
PROJECT NAME | FoodBridge
Project Members | مريم القحطاني
غلا الصويان
البتول حافظ
ريناد العبداني
DATE | 27/09/2026 – 06/10/2026 (Phase 1)

## WEEK 1
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday | Saturday
Date |  | 27/09/2026 (Sunday) Scrum Meeting 1 | 28/09/2026 (no meeting) | 29/09/2026 (Tuesday) Scrum Meeting 2 | 30/09/2026 (no meeting) | 01/10/2026 (Thursday) Scrum Meeting 3 | 03/10/2026 (Saturday) Scrum Meeting 4 (online – WhatsApp)
Attendees |  | مريم القحطاني غلا الصويان البتول حافظ ريناد العبداني Facilitator: البتول حافظ | No meeting | مريم القحطاني غلا الصويان البتول حافظ ريناد العبداني Facilitator: البتول حافظ | No meeting | مريم القحطاني غلا الصويان البتول حافظ ريناد العبداني Facilitator: البتول حافظ | مريم القحطاني غلا الصويان البتول حافظ ريناد العبداني Facilitator: البتول حافظ
Key discussion points |  | Agreed on the product idea (FoodBridge) and its target users. Assigned the Scrum roles. Agreed to meet at least every 2 days and to use one WhatsApp group for daily communication. Each member writes 4 User Stories in her area. | — | Reviewed the Vision Statement draft. Agreed on one User Story format. Discussed which donor profile fields are mandatory and which are optional. | — | Reviewed all 16 User Stories in the Product Backlog. Agreed to order the backlog by customer value. Discussed the candidate Sprint 1 stories and the plan for the DEEP check. | Online meeting in the team WhatsApp group. Gave feedback on the Sprint Goal draft. Discussed the story points of the larger stories (US09, US13, US14 and US15).
مريم القحطاني (Product Owner) | What did you do since the last meeting? | Formulated the core product idea and identified the target stakeholders. | — | Drafted the Vision Statement and the target audience profiles. | — | Finished the 4 donor User Stories (US01-US04), decided the donor profile fields and finalized the Vision Statement. | Prioritized all Product Backlog Items and sent the final order to Renad.
| What are you doing today? | Draft the Vision Statement and the target audience profiles. | — | Write the donor-related User Stories (US01-US04). | — | Prioritize all Product Backlog Items based on customer value and project needs. | Answer the team questions about the priorities and review the Sprint Goal draft.
| Is there anything blocking you? | None. | — | Need to decide the mandatory vs optional fields for the donor profile. | — | None. | None.
غلا الصويان (Development / QA) | What did you do since the last meeting? | Participated in the initial team brainstorming and role setup. | — | Drafted the 4 charity-related User Stories (US05-US08). | — | Refined the charity User Stories (US05-US08). | Reviewed the prioritized Product Backlog and drafted the Sprint Goal and the candidate Sprint 1 stories.
| What are you doing today? | Draft the charity-related User Stories (US05-US08). | — | Review and refine the charity User Stories. | — | Review the prioritized Product Backlog with the team, propose the Sprint Goal and select the candidate Sprint 1 User Stories. | Share the Sprint Goal draft in the group and update it based on the feedback.
| Is there anything blocking you? | None. | — | None. | — | None. | None.
البتول حافظ (Scrum Master) | What did you do since the last meeting? | Set up the team communication channel and the Scrum meeting schedule. | — | Facilitated Scrum Meeting 1 on Sunday and logged the team updates. | — | Finished the 4 donation process and tracking User Stories (US09-US12) in the agreed format. | Updated the Daily Scrum log and followed up on the open blockers.
| What are you doing today? | Facilitate this first Scrum meeting and record the team updates. | — | Draft the donation process and tracking User Stories (US09-US12). | — | Update the Daily Scrum log and follow up on the open blockers. | Collect the team feedback on the Sprint Goal draft in the WhatsApp group.
| Is there anything blocking you? | None. | — | Minor format differences between the members' User Story drafts. | — | None. | None.
ريناد العبداني (Development / QA) | What did you do since the last meeting? | Reviewed the project requirements and the DEEP criteria guidelines. | — | Drafted the admin and supporting User Stories (US13-US16) and set up the Product Backlog Excel file. | — | Collected all 16 User Stories into the Product Backlog and unified their format. | Started validating the User Stories against DEEP and adding the Story Points.
| What are you doing today? | Draft the admin and supporting User Stories (US13-US16) and prepare the Product Backlog Excel file. | — | Collect the User Stories that are ready and unify their format. | — | Validate all 16 User Stories against the DEEP criteria and add the Story Points with the team. | Continue the DEEP validation and the Story Points.
| Is there anything blocking you? | None. | — | Waiting for the remaining User Stories and the Product Owner's priorities. | — | None. | Need the team to agree on the Story Points of the larger stories.
Action items |  | 1) Each member drafts her 4 User Stories before the next meeting. 2) Maryam shares the Vision Statement draft on Tuesday. | — | 1) All User Stories use one format: "As a ..., I want to ..., so that ...". 2) Maryam and Albatool send their stories to Renad by Thursday. 3) Maryam decides the donor profile fields. | — | 1) Maryam sends the final priority order to Renad. 2) Ghala shares the Sprint Goal draft in the team WhatsApp group on Saturday. 3) Next meeting: Saturday 03/10/2026 online (WhatsApp). | 1) The team agrees on the Story Points of US09, US13, US14 and US15 in the group today. 2) Ghala brings the updated Sprint Goal to the Sunday meeting.

## WEEK 2
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday | Saturday
Date |  | 04/10/2026 (Sunday) Scrum Meeting 5 | 05/10/2026 (no meeting) | 06/10/2026 (Tuesday) Scrum Meeting 6 | 07/10/2026 (no meeting – submission day) | 08/10/2026 (after Phase 1 submission) | 10/10/2026 (after Phase 1 submission)
Attendees |  | مريم القحطاني غلا الصويان البتول حافظ ريناد العبداني Facilitator: البتول حافظ | No meeting | مريم القحطاني غلا الصويان البتول حافظ ريناد العبداني Facilitator: البتول حافظ | No meeting | No meeting | No meeting
Key discussion points |  | Confirmed the Sprint 1 stories (US01, US02, US03, US05, US06). Agreed to keep the low-priority stories as epics. Discussed the overlap between US04, US10 and US12 and the hour estimates for the database tasks. | — | Decided that a new charity account is Active in Sprint 1 because admin approval (US13) is in Sprint 2. Balanced the task hours and made sure each feature is tested by a member who did not build it. Final check of all Phase 1 files before submission. | — | — | —
مريم القحطاني (Product Owner) | What did you do since the last meeting? | Answered the team questions on the priorities and confirmed the Sprint 1 stories: US01, US02, US03, US05 and US06. | — | Approved the final Product Backlog order and the User Story wording. | — | — | —
| What are you doing today? | Review the DEEP results and confirm that the low-priority items stay as epics. | — | Do a final review of the Vision Statement and the Product Backlog before submission. | — | — | —
| Is there anything blocking you? | None. | — | None. | — | — | —
غلا الصويان (Development / QA) | What did you do since the last meeting? | Finalized the Sprint 1 Goal after the team feedback on Saturday and selected the Sprint 1 User Stories. | — | Finished the task breakdown, the hour estimates and the Definition of Done. Balanced the task hours between the members. | — | — | —
| What are you doing today? | Break the Sprint 1 User Stories into technical tasks, estimate the hours and draft the Definition of Done. | — | Finalize the Sprint 1 Backlog (dated 10/06/2026). | — | — | —
| Is there anything blocking you? | Estimating realistic hours for the backend database tasks. | — | None. | — | — | —
البتول حافظ (Scrum Master) | What did you do since the last meeting? | Logged the Saturday WhatsApp meeting and followed up on the blockers. | — | Ran the estimation review. The team agreed that a new charity account is Active in Sprint 1, because admin approval (US13) comes in Sprint 2. | — | — | —
| What are you doing today? | Organize a short estimation review with the whole team to help with the task hours. | — | Prepare the meeting summary and check that all Phase 1 files are consistent. | — | — | —
| Is there anything blocking you? | None. | — | None. | — | — | —
ريناد العبداني (Development / QA) | What did you do since the last meeting? | Validated the 16 User Stories against DEEP, added the Story Points and ordered the Product Backlog by the Product Owner's priorities. | — | Wrote US12-US15 as epics, clarified US04, US10 and US12, and updated the Number of Sprints column. | — | — | —
| What are you doing today? | Write the low-priority stories (US12-US15) as epics and clarify the overlap between US04, US10 and US12. | — | Do a final check of the Product Backlog (names, IDs and sprint numbers). | — | — | —
| Is there anything blocking you? | None. | — | None. | — | — | —
Action items |  | 1) Team estimation review for the Sprint 1 tasks (organized by Albatool). 2) Testing of each feature is assigned to a member who did not build it (DoD point 3). | — | 1) Submit all Phase 1 files by Wednesday 07/10/2026. 2) Sprint 1 starts on 07/10/2026. | — | — | —

## WEEK 3
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?

## WEEK 4
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?

## WEEK 5
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?

## WEEK 6
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?

## WEEK 7
DAILY SCRUM
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?
[Name] | What did you you do yesterday?
What are doing today?
Is there anything blocking you?