## Sprint 1
FoodBridge - SPRINT 1 BACKLOG
CURRENT DATE | SPRINT START DATE | TOTAL ASSIGNED HOURS |  | HOURS USED |  | HOURS REMAINING
10/06/26 | 10/07/26 | 57 |  | 0 |  | 57
SPRINT GOAL | Donors and charities can open their accounts, and a donor can post a surplus food donation that appears to charities in the available donations list.
SPRINT TRACKING |  |  |  |  | Start of the Sprint Date | 10/07/26
User Stories and Tasks | ASSIGNED TO | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14
US01 Donor registration |  | 13 | 0 | 13
T1.1 Create the Flask project, the folders and the SQLite database file | Maryam Alqahtani | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1.2 Create the users table (name, email, password, phone, role) | Maryam Alqahtani | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1.3 Build the donor registration page | Albatool Hafez | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1.4 Save the donor record and hash the password | Albatool Hafez | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T1.5 Test registration with empty fields and a repeated email | Renad Alabdani | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 Charity registration |  | 10 | 0 | 10
T2.1 Create the charities table (organization name, license number, city, address) | Maryam Alqahtani | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2.2 Build the charity registration page | Ghala Alsowayan | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2.3 Save the charity record as Active for Sprint 1 (admin approval is added later with US13) | Renad Alabdani | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2.4 Test charity registration | Albatool Hafez | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 User login |  | 9 | 0 | 9
T3.1 Build the login page | Ghala Alsowayan | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3.2 Check the email and password and open a session | Albatool Hafez | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3.3 Redirect each role to its own home page after login | Ghala Alsowayan | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T3.4 Test login (wrong password, charity vs donor) | Renad Alabdani | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 Add food donation |  | 15 | 0 | 15
T4.1 Create the donations table (food type, quantity, expiry time, pickup address, status) | Maryam Alqahtani | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4.2 Build the add donation form | Ghala Alsowayan | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4.3 Save the donation with status Available and link it to the donor | Renad Alabdani | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4.4 Validate the form (quantity above zero, expiry time in the future) | Renad Alabdani | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T4.5 Test adding a donation | Albatool Hafez | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US06 Browse available donations |  | 10 | 0 | 10
T5.1 Build the available donations list page for charities | Ghala Alsowayan | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5.2 Query only the donations with status Available and not expired | Maryam Alqahtani | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5.3 Show a message when the list is empty | Ghala Alsowayan | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T5.4 Test the list with expired and collected donations | Renad Alabdani | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  | 57 | 0 | 57
DEFINITION OF DONE
1. The task is merged into the main branch of the team repository.
2. The page runs locally with Flask without any error message.
3. Another member tried the feature and it did what the user story says.
4. Wrong input is handled with a clear message instead of a crash.
5. The database changes are written in the schema file so every member gets the same tables.